IPAAS PLATFORM — BUILD PLAN

Phase 1: Foundation  →  Phase 2: Self-Service Onboarding

August 25 – October 15, 2026  ·  Prepared by Raj Kamal

# 1. Purpose

A single, sequenced build plan for the iPaaS platform's POC/implementation, using OculusIT (ConnectWise → Keka) as the concrete use case. Phase 1 builds the foundation: the platform can automatically stand up a tenant's dedicated sync environment, and the canonical model supports the full OculusIT entity set. Phase 2 extends that foundation into an actual self-service platform: real-time sync, and a UI a tenant can configure themselves rather than engineering hand-provisioning them.

# 2. Scope — Two Phases

| Phase | Components | Target |
| --- | --- | --- |
| Phase 1 | Platform/Infra — CI/CD, Canonical Model (Mapping & Transformation Engine), Provisioning Engine | Aug 25 – Sept 15, 2026 (3 weeks) |
| Phase 2 | Orchestration Engine (extend to Project/Timesheet), Event & Queue Layer (real-time), API Layer (self-service config), Client/Admin UI (minimal) | Sept 15 – Oct 15, 2026 (4 weeks) |

Phase 1 deliberately builds the infrastructure and data-model foundation first — a published image, an automated way to stand up a tenant environment from it, and a canonical model that covers the full OculusIT entity set. Phase 2 then extends the running Orchestration Engine to actually use that foundation for live sync, and wraps the whole thing in a self-service configuration surface.

# 3. Phase 1 — Week-by-Week (Aug 25 – Sept 15)

| Week | Focus | Deliverables |
| --- | --- | --- |
| Week 1 Aug 25 – 31 | CI/CD Pipeline | Write a Dockerfile for the Node app GitHub Actions workflow: build, tag (git SHA), push to a container registry on merge to main In parallel: begin the canonical schema definition for Project and Timesheet Exit: a merge to main produces a pullable, versioned image; canonical schema drafted |
| Week 2 Sept 1 – 7 | Canonical Model | Author inbound mapping profiles: ConnectWise → canonical (Project, Timesheet) Author outbound mapping profiles: canonical → Keka (Project, Timesheet) Dry-run validation against real sample payloads from both systems Begin the Provisioning Engine: image-selection logic against the registry built in Week 1 Exit: mapping profiles live in Postgres, passing dry-run tests |
| Week 3 Sept 8 – 15 | Provisioning Engine | Finish the Provisioning Engine: reads a tenant's saved configuration, selects the published image, triggers CI/CD to stand up that tenant's dedicated Orchestration Engine container Integration test: provision OculusIT's environment from its configuration and confirm the container runs the existing Client-entity sync correctly Demo prep Exit: a tenant's dedicated sync container can be stood up automatically from saved configuration and a published image |

# 4. Phase 2 — Week-by-Week (Sept 15 – Oct 15)

| Week | Focus | Deliverables |
| --- | --- | --- |
| Week 4 Sept 15 – 21 | Sync Execution | Extend the Orchestration Engine's fetch/retry/checkpoint loop to Project and Timesheet, using the mapping profiles built in Phase 1 Implement entity dependency ordering (Client → Project → Timesheet) Validate Keka write() live for Project and Timesheet — first live check Add a dead-letter table (tenant-scoped, same Postgres) — when retries exhaust on a record, persist it there with the error reason and payload instead of silently dropping it Exit: full Client → Project → Timesheet sync running scheduled + one-time, inside the provisioned container, checkpointed, retried, and failed records captured for review |
| Week 5 Sept 22 – 28 | Real-Time Sync (Minimal) | Build one webhook receiver endpoint (ConnectWise) Wire the webhook trigger directly into the Orchestration Engine — no message broker (Valkey/BullMQ) for this phase, by design; failed records still land in the Week 4 dead-letter table End-to-end integration test: ConnectWise change → webhook → sync → Keka write, all 3 entities Exit: live real-time sync working end-to-end, with failures captured, not silently dropped |
| Week 6 Sept 29 – Oct 5 | Configuration API | API endpoints: provider selection, model selection (reads from the Mapping Engine's per-provider registry), sync mode, sync type (one-way only, enforced server-side) Persist configuration to Data & Secrets Store, tenant-scoped Exit: a full config payload can be submitted and retrieved via API for a given tenant |
| Week 7 Oct 6 – 15 | Minimal UI + Integration | Minimal Angular UI: login, provider/model selection, sync mode/type selection, submit Wire UI → API Layer → Provisioning Engine end-to-end Integration test: onboard a brand-new tenant through the UI alone, with no manual backend step Demo prep Exit: a new tenant can self-configure and get a running, syncing environment without engineering involvement |

# 5. Demo Outcomes

## End of Phase 1 (Sept 15)

OculusIT's environment is stood up automatically — the Provisioning Engine reads its saved configuration, pulls the CI/CD-published image, and brings up a dedicated container running the existing, already-proven Client-entity sync. Separately, the canonical model now has validated mapping profiles for Project and Timesheet.

What this demo will not include yet: Project and Timesheet don't actually sync live inside that container — the mapping profiles are built and dry-run validated, but the Orchestration Engine isn't wired to execute them until Phase 2, Week 4. Worth stating plainly so the two aren't conflated.

## End of Phase 2 (Oct 15)

A new tenant logs into the UI, picks ConnectWise and Keka, picks the entities and sync mode, and submits. Minutes later, without any manual backend step, that tenant has a running environment syncing Client, Project, and Timesheet — on schedule and in real time. This is the full loop: self-service configuration through automated provisioning through live, working sync.